## Central_Tracker
SR.NO | Activity | Technology | Activity Driven By | Start Date | Status | Activity Description | Completion Date
1 | Selecting AUT | Project Management | ALL | 13/7/2022 | Completed | Going through different sources to find AUT | 17/7/2022
2 | Problem Statement | Project Management |  | 15/7/2022 | Completed | Finalizing Problem Statement | 20/07/2022
3 | Git Implemetation | GIT | ALL | 2022-01-10 | Completed | Creating repositories and setting it up on PSL Machines | 2022-04-08
4 | Manual Test Case Writing | Manual Testing | ALL | 15/7/2022 | Completed | Writing Manual Test cases for all the pages | 20/07/2022
5 | Meeting for manual testcases query | Project Management |  | 19/07/2022 | Completed | Reviewing the Manual Test Cases | 23/07/2022
6 | Status Accounting Meeting | Project Management |  | 27/08/2022 | Completed | Status Accounting meeting with Anuprita & Varsha | 29/08/2022
7 | Meeting for manual testcases finalization | Project Management |  | 30/07/2022 | Completed | Finalizing merged Manual Test Cases | 2022-03-07
8 | Automating Test Cases | Selenium |  | 22/08/2022 | Completed | Automating Manual Test Cases using Selenium with Java | 2022-06-09
9 | Creating Daily Activity Tracker | Project Management |  | 26/08/2022 | Completed | Creating Activity Tracker | 28/08/2022
10 | Scrum Meetings | Project Management |  | 28/08/2022 | Completed | Daily Scrum Meetings | 30/08/2022
11 | Status Accounting Meeting 2 | Project Management |  | 31/08/2022 | Completed | Review tracker, manual test cases and selenium code | 2022-03-09
12 | REST API Testing Distribution | Project Management |  | 2022-02-10 | Completed | Distributed the REST API Testing modules | 2022-04-10
13 | Rest Api Implementation in Postman | Rest_API_Postman |  | 2022-02-10 | Completed | Writing Manual Test cases and automating using postman | 2022-04-10

## Project_Management
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Selecting AUT
1 | Selected AUT | All | 2022-11-07 | Completed | Difficulty Finding project satisfying all the criterias | Exhaustive Searching | 2022-11-07
Problem Statement
1 | Problem Statement 1.0 Creation | ALL | 2022-12-07 | Completed | Unavailablity of Template | Created our own template | 2022-12-07
API Feasibility Check
1 | Git Implementation | ALL | 28/09/2022 | Completed |  | Creating repositories and setting it up on PSL Machines | 2022-02-10
SYNC UP Meetings
1 | Meeting for manual testcases query | ALL | 13/07/2022 | Completed |  |  | 13/07/2022
2 | Meeting for manual testcases finalization | ALL | 30/07/2022 | Completed |  |  | 30/07/2022
Project Related Activites
1 | Created index page and added hyperlinks for manual testcases | Simran Mujawar | 15/07/2022 | Completed |  |  | 15/07/2022
|  | Dipti Sadale | 15/07/2022 | Completed |  |  | 15/07/2022
Scrum Meetings
1 | Application & Problem statement | Sanmati Porlekar | 26/08/2022 | Completed |  |  | 26/08/2022
2 | Application selection | Sneha Demanna | 27/08/2022 | Completed |  |  | 27/08/2022
3 | Setup On PSL | Sai Surya Teja | 28/08/2022 | Completed |  |  | 28/08/2022
4 | Problem statement 2.0 | Harshitha Bollineni | 30/08/2022 | Completed |  |  | 29/08/2022
Manual Testing
1 | Test Case | ALL | 21/07/2022 | Completed |  |  | 21/07/2022
2 | Test Scenario | ALL | 21/07/2022 | Completed |  |  | 21/07/2022
3 | ECP-BVA report | Ayushi Chaurasia | 17/07/2022 | Completed |  |  | 16/07/2022
4 | Defect report | Vishakha Mane | 27/07/2022 | Completed |  |  | 28/07/2022
5 | Execution log report | Simran Mujawar | 30/07/2022 | Completed |  |  | 30/07/2022
6 | functional requirements | Venkat Lakshaman | 15/07/2022 | Completed |  |  | 14/07/2022
7 | Non-functional requirements | Venkat Lakshaman | 15/07/2022 | Completed |  |  | 14/07/2022
Rest_API_Postman
1 | Find the API for OrangeHRM | Simran Mujawar | 2022-02-10 | Completed | Finding the fake API for OrangeHRM | Used the API for other ecommerce websites.****** | 2022-03-10
2 | Testing using methods like POST, GET. | Simran Mujawar | 2022-02-10 | Completed | Status code for POST is …......**** | Use of fake API lead to the issue. Actual Data insertion wont take place. Hence 200 OK wont be an error.**** | 2022-03-10
Selenium
1 | Writing automation script for Login, Forgotpassword, Forgotlogin​ | Sai Surya Teja | 25/08/2022 | Completed |  |  | 2022-05-09
2 | Writing automation scripts for admin page | Sai Surya Teja | 25/08/2022 | Completed |  |  | 2022-05-09
Venkat Lakshman
3 | Writing automation scripts for PIM Page | Sai Surya Teja | 25/08/2022 | Completed |  |  | 2022-05-09
Venkat Lakshman
2022-05-09
4 | Writing automation script for Leave page | Sanmati Porlekar | 25/08/2022 | Completed
|  | Simran Mujawar |  |  |  |  | 2022-05-09
5 | Writing automation script for Time page | Sanmati Porlekar | 25/08/2022 | Completed
2022-05-09
6 | Writing automation scripts for Recruitment | Sneha Demanna | 25/08/2022 | Completed
7 | Writing automation scripts for My Info | Sneha Demanna |  | Completed
8 | Writing automation scripts for Performance | Dipti Sadale |  | Completed
9 | Writing automation scripts for Directory | Harshitha Bollineni |  | Completed

## GIT
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Git Implementation
1 | Created local repository | Sanmati Porlekar | 2022-01-10 | Completed | NA | NA | 2022-01-10
2 | Files uploaded to repository | Dipti Sadale | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Simran Mujawar | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Sneha Demanna | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Ayushi Chaurasia | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Sai Surya Teja | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Harshitha Bollineni | 28/09/2022 | Completed | NA | NA | 2022-02-10
|  | Venkat Lakshman |  | Completed | NA | NA

## Manual_Testing
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Manual Test Case Writing
1 | Creating Test Cases and test Scenario for "Login page" | Sai Surya Teja | 20/07/2022 | Completed | NA | NA | 21/07/2022
2 | Creating Test Cases and test Scenario for "admin page" | Sai Surya Teja & Venkat Lkashman | 20/07/2022 | Completed | NA | NA | 21/07/2022
3 | Creating Test Cases and test Scenario for "PIM page" | Sai Surya Teja & Venkat Lkashman | 20/07/2022 | Completed | NA | NA | 21/07/2022
4 | Creating Test Cases and test Scenario for "Leave page" | Simran Mujawar & Sanmati Porlekar | 20/07/2022 | Completed | NA | NA | 21/07/2022
5 | Creating Test Cases and test Scenario for "Time page" | Sanmati Porlekar | 20/07/2022 | Completed | NA | NA | 21/07/2022
6 | Creating Test Cases and test Scenario for "Recruitment page" | Sneha Demanna | 20/07/2022 | Completed | NA | NA | 21/07/2022
7 | Creating Test Cases and test Scenario for "My Info" | Sneha Demanna | 20/07/2022 | Completed | NA | NA | 21/07/2022
8 | Creating Test Cases and test Scenario for "Performance page" | Dipti Sadale | 20/07/2022 | Completed | NA | NA | 21/07/2022
9 | Creating Test Cases and test Scenario for "Directory page" | Harshitha Bollineni | 20/07/2022 | Completed | NA | NA | 21/07/2022
12 | Creating ECP-BVA report | Ayushi Chaurasia | 15/07/2022 | Completed | NA | NA | 16/07/2022
13 | Creating Execution log report | Simran Mujawar | 27/07/2022 | Completed | NA | NA | 28/07/2022
14 | Creating Defect report | Ayushi Chaurasia | 29/07/2022 | Completed | NA | NA | 30/07/2022
15 | Creating Functional requirements | Venkat Lakshman | 14/7/2022 | Completed | NA | NA | 14/7/2022
16 | Creating Non-Functional requirements | Venkat Lakshman | 14/7/2022 | Completed | NA | NA | 14/7/2022

## Selenium
SR.NO | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Automating Test Cases
1 | Writing automation script for Login, Forgotpassword, Forgotlogin​ | Sai Surya Teja | 25/08/2022 | completed |  |  | 2022-05-09
2 | Writing automation scripts for admin page | Sai Surya Teja | 25/08/2022 | completed |  |  | 2022-05-09
Venkat Lakshman
3 | Writing automation scripts for PIM Page | Sai Surya Teja | 25/08/2022 | completed |  |  | 2022-05-09
Venkat Lakshman
|  |  | 25/08/2022 | completed |  |  | 2022-05-09
4 | Writing automation script for Leave page | Sanmati Porlekar
|  | Simran Mujawar | 25/08/2022 | completed |  |  | 2022-05-09
5 | Writing automation script for Time page | Sanmati Porlekar
|  |  | 25/08/2022 | completed |  |  | 2022-05-09
6 | Writing automation scripts for Recruitment | Sneha Demanna
7 | Writing automation scripts for My Info | Sneha Demanna
8 | Writing automation scripts for Performance | Dipti Sadale
9 | Writing automation scripts for Directory | Harshitha Bollineni

## Rest_API_Postman
SR NO. | Activity | Activity Driven By | Start Date | Status | Blockers | Steps Taken to Resolve | Completion Date
Rest API Implementation in Postman
1 | Find the API for OrangeHRM | Simran Mujawar | 2022-01-10 | completed | Finding the fake API for OrangeHRM | Used the API for other ecommerce websites. | 2022-03-10
2 | Testing using methods like POST, GET. | Simran Mujawar | 2022-01-10 | Completed | Status code for POST is …..... | Use of fake API lead to the issue. Actual Data insertion wont take place. Hence 200 OK wont be an error. | 2022-02-10